## HVR
Category of Task | Action Item | Time Frame | Deadline | Volunteer(s) | Status | Comments
Nomination Process (Late January - 3/31) | Send email to MyTRB@nas.edu asking to open the website with a deadline of 3/31 11:59 Eastern for submissions | Last week in January | 1/30 | Cindy | Done | a4rtfgv
| Send email to RAC listserv with deadlines (3/31 at 11:59 E--no exceptions) and instructions. | Early February | 2/2 | Cindy | Done | Email sent to RAC listserv on Friday, 1/23/26
| Send reminders every couple of weeks during the nomination process | Early February through March 31 | Last one 3/31 | Cindy | Ongoing | Ongoing
| Help RAC members with project nomination and website entry | Early February through March 31 | 3/31 | Cindy | Ongoing | Ongoing
| Deadline for HVR website project nominations | Firm deadline of 3/31 | 3/31--11:59 Eastern Time, no exceptions | Cindy
| Export projects from HVR website | First week in April | 4/6 | Cindy
| Determine second Honorable Mention award category from National Study Codes entered into HVR projects | First week in April | 4/10 | Cindy/Mike Fitch
Voting Process (early April - Mid-May) | Send lists of projects to Region Chairs for voting coordination by May 15, along with announcement of 2nd Honorable Mention subject area. Each region will vote for their top 4 main HVR, along with the top 2 in Safety, and top 2 in the second Honorable Mention area | Early - Mid April | 4/13 | Jenni
| Region voting on their top 4 HVR (top 6 for R4), top 2 Honorable Mention Safety, and top 2 for 2nd Shonorable Mention area | Mid-April - May 22 | 5/22 | Region Chairs
| Send congratulatory email announcing HVR and Honorable Mention winners to RAC listserv | Week of 5/26 - 5/29 | 5/29 | Wade
| Check the winners off in the HVR website. Go to Projects, filter, and edit each winner individually by checking either the HVR/Sweet 16 or Honorable Mention checkbox. | Late May/Early June | 6/12 | Brian/Cindy
RAC Summer Meeting | Coordinate with summer meeting planning region/group and RAC Chair and Vice Chair for any RAC summer meeting HVR events or showcases--the 2023 RAC summer meeting will feature only poster sessions, HVR only, no Honorable Mention | Early to Mid-June (to have in time for printing meeting agendas) | 6/12 | Brian
| Notify winners for summer meeting poster session, including dimensions and guidelines from hosting region and AASHTO (depends on available space). Ask who will be presenting. Normally it's the state DOT person; however, if the project is near the meeting, they might come and present. | Mid-June deadline but continue assistance | 6/12
| Send list of projects by region, including the state DOT and title, to hosting region leadership for inclusion in the final agenda. This is HVR only; Honorable Mentions are not showcased at the RAC summer meeting. | Mid-June or agenda-printing deadline | 6/12
| Assist poster session presenters during the meeting. Must be 2' x 3' per AASHTO | Late July--Meeting time |  |  | Posters must be 2' x 3' per AASHTO
| Use the Power Point template to create certificates for winning HVR and Honorable Mention Award projects. | Mid-June through mid-July | 6/30 | Sally
| Get certificates printed. | Mid-June through mid-July | 6/30 | Sally
| Get certificates signed by RAC Chair and VOR Co-Chairs. | Mid-June through mid-July | At meeting
| Bring or ship certificates to summer meeting hotel, or to someone who can carry them to the meeting. | Late June/early July
TRB Annual Meeting 2027 Poster Sessions | Coordinate with TRB liaison to learn dates/times for HVR poster sessions (one for HVR and one for Honorable Mention awards) | August-September | 9/1
| Notify winning HVR and Honorable Mention Award state DOTs about poster sessions. Ask them to send you info whether they will present, who will present, project title, PI(s), and short summary of the project. Include links from TRB about poster session guidelines. | 9/15 deadline (to allow time for next task) | 9/15
| Gather/Retrieve information from winners and make table/list....presenters, POC, etc. | September | September/October
| Enter poster session information into TRB system or coordinate with TRB on this. | 9/15 - 10/1 | 10/1
| TRB will send information and guidance to presenters, but it's a good idea to have a VOR person for them to contact with questions. | October - Early January | 11/15 (or whenver TRB final agenda is published) for CV to reach out
| Send email to RAC and RIIM about poster sessions. RIIM Chair will normally send out an email about salient research- and innovation-oriented sessions to attend. | October - Early January | 11/15 or as requested by TRB Support Staff
| Assist if necessary with getting posters to TRB | Late December - Early January | First week of January
| Preside at the poster sessions | January | TBD for 2027 | Mike Fitch