Updated 10/17/19

Conference Planner (CP)		Host State (HS)		Program Committee (PC)

January - June 2019

- Select meeting venue/hotel after conducting site visits –Marriott in Newton, MA

- Select meeting date – July 19-23, 2020

- Establish a schedule of meeting planning calls (host state, region, meeting planners) 3rd Thursday every month at 1:30PM EST

- Get budget from AASHTO and set registration fee

September 2019

- Develop save the dates and invites/flyers – HS Lily provided the flyer and PC approved

- E-mail save the date flyers to RAC – HS Lily will send out to RAC Listserv

- Identify potential sponsors and sponsorship levels and provide the list to AASHTO Conference Planner – HS & PC

- Provide AASHTO with basic level agenda with meals, activities, etc (used for budgeting) – PC Emily will send to Karen (CP)

- Set up conference website (basic ‘save the date’ page and notices go live) – CP Lily provided a photo for the website page

October 2019

- Develop meeting theme and get RAC leadership approval – PC - NA

- Identify content for website, including theme, host city, and other notices – HS & PC

- Develop detailed meeting information to R&I/RAC website page (i.e. registration, hotel, and travel info) – CP

- Identify keynote speakers for the general sessions – HS & PC MassDOT Secretary and FHWA Division Administrator

November 2019

- Consult with RAC Leadership and TF Chairs for their expectations of regularly scheduled program items - PC

- Consult with TRB Liaison to RAC regarding the expectations for the TRB State Rep session – PC

December 2019

- Secure venue for Monday Welcome Reception and Tuesday off-site event/dinner – HS & CP

- Update website with options for local restaurants, attractions, links to host city map and transportation options - CP

- Create invitation lists

- Contact Visitors Bureau (graphics, photos, maps, trinkets) – HS

January 2020

- Provide a 5-10 min presentation to highlight the meeting/location during the RAC Winter Meeting at TRB – HS and/or Host Region

- Finalize sessions and assign session coordinators  - PC

- Identify someone to coordinate conference attendee bags – HS

February 2020

- Publish meeting agenda to website (provided by PC) – CP

- Registration website front page live

- E-mail RAC with the registration website information – HS

- Finalize meeting room assignments - CP

March 2020

- Coordinate all arrangements with exhibitors and communicate all rules and regulations pertaining to exhibitors (if appropriate) – PC & CP

- Identify options for Regional Breakout dinners and send information to the RAC regional chairs - HS

April 2020

- Finalize the list of items for the conference attendee bags - HS

- Coordinate A/V/Internet Access – PC & CP

- Coordinate transportation to off-site events included in the registration fee (if not in walking distance) – HS & CP

May 2020

- Recruit and train meeting staff/volunteers – HS & CP

- Identify volunteers from MassDOT for the registration table/IT – HS

- Confirm all presentations and speakers and add all names to the agenda - PC

- Begin creating session summary pages for moderators and speakers - PC

June 2020

- Finalize session summary pages for the final agenda - PC

- Request PDH’s from AASHTO’s Engineering Division (if appropriate)

- Collect and review all presentations to ensure quality, continuity, and eliminate duplication of remarks - PC

July 2020

- Publish meeting program/agenda with speaker names - CP

- Print meeting signage - CP

- Publish final copy of all promotional literature for the meeting to website - CP

- Print all promotional literatures for meeting - CP

- Track prepaid and on-site registrations - CP

- Print list of participants - CP

- Print nametags and speaker name tents - CP

- Provide registration packets & promotional items (if appropriate) - HS

- Provide hotel and other function areas with up-to-date head count for food - CP

- Provide tickets for meals & other outings (if appropriate) - CP

- Process all attendee registrations, collect fees, and pay meeting bills - CP

- Provide a spouse/guest program (if appropriate)  - CP

- Confirm date/time/location with speakers and provide information for registration – PC

August

- Solicit meeting feedback (e.g. evaluation forms & surveys) –Admin TF will handle

- Collect and summarize meeting feedback - Admin TF will handle

- Send Thank You notes to speakers and moderators - PC

#### Program Committee Responsibilities (Committee is chaired by and includes the other states in Region 1)

- Schedule monthly conference calls; coordinate to ensure updates are ready for monthly RAC officers’ calls (ongoing)

- Develop meeting theme    (October

- Develop session topics (November thru January)

- Establish session format (panel, town hall, individual speakers, etc.) (November thru February)

- Secure keynote and other general session speakers (October)

- Secure and coordinate session planners and moderators (January thru April)

- Set agenda (May)

- Collect speaker and moderator bios (June)

- Provide instructions to speakers and the session moderator regarding topic, length of presentation, format, etc. (June)

- Coordinate handouts (June)

#### Session Moderator Responsibilities

- Contact presenters in designated session for introductions or special notes as needed

- Introduce speakers

- Develop time keeping method to keep on track with agenda

- Check to see that speakers’ presentations are loaded and working properly prior to session

- Help distribute handouts if necessary

- Orchestrate audience Q&A; be prepared with a few questions to start the process if necessary

- Identify a note taker